## Decs
Town & Country - 2025/26 Works Programme |  | as at 05/12/25
REDECORATION WORKS
Key:
In Progress
Estimated Start
Complete
[5 empty] | Week1 | Week2 | Week3 | Week4 | Week5 | Week7 | Week8 | Week9 | Week10 | Week11 | Week12 | Week13 | Week14 | Week15 | Week16 | Week17 | Week18 | Week19 | Week20 | Week21 | Week22 | Week23 | Week24 | Week25 | Week26 | Week27 | Week28 | Week29 | Week30 | Week31 | Week32 | Week33 | Week34 | Week35 | Week36 | Week37 | Week38 | Week39 | Week40 | Week41 | Week42 | Week43 | Week44 | Week45 | Week46 | Week47 | Week48 | Week49 | Week50 | Week51 | Week52 | Week53
Property | Start Date | End Date | Duration | Status / comment | 2025-04-07 | 2025-04-14 | 2025-04-21 | 28/04/25 | time axis 2025-05-05 to 2026-03-30
Lincoln Walk - Houses | 28/04/25 | 19/05/25 | 3 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Dorset Square - Houses | 28/04/25 | 19/05/25 | 3 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Eleanor Avenue - Houses | 28/04/25 | 19/05/25 | 3 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Cumberland Close - Houses | 28/04/25 | 19/05/25 | 3 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Rutland Close - Houses | 28/04/25 | 19/05/25 | 3 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Ormonde Avenue - Houses | 28/04/25 | 17/06/25 | 6.5 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Bishopsmead Close - Houses | 06/05/25 | 09/06/25 | 5 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Hollymoor Lane - Houses | 06/05/25 | 09/06/25 | 5 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Cotherstone - Houses | 06/05/25 | 10/06/25 | 5.5 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Melton Place - Houses | 06/05/25 | 10/06/25 | 5.5 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Hyperion Place - Houses | 06/05/25 | 11/06/25 | 5.5 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Somerset Close - Houses | 20/05/25 | 04/06/25 | 2 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Almond Road - Houses | 20/05/25 | 09/06/25 | 2 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Trigo Court - Houses | 20/05/25 | 13/06/25 | 3 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Watersedge - Houses | 26/05/25 | 20/06/25 | 4 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Ash Cottages - Houses | 26/05/25 | 09/06/25 | 2 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Bourne Way - House | 26/05/25 | 02/06/25 | 1 week | Complete |  |  |  |  | 2025-12-22: Christmas Break
Cherwell Court - Houses | 27/05/25 | 10/06/25 | 2 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Crane Court - Houses | 27/05/25 | 17/06/25 | 2.5 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Lansdowne Road - House | 27/05/25 | 10/06/25 | 2 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Shawford Road - Houses | 28/05/25 | 13/06/25 | 2.5 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Belfield Road - Houses | 28/05/25 | 13/06/25 | 2.5 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Gatley Avenue - Houses | 29/05/25 | 12/06/25 | 2 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Iris Court - House | 30/05/25 | 13/06/25 | 2 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Scott Close - Houses | 02/06/25 | 18/06/25 | 2.5 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Fendall Road - Houses | 02/06/25 | 18/06/25 | 2.5 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Brumfield Road - Houses | 03/06/25 | 17/06/25 | 2 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Gadesden Road - Houses | 03/06/25 | 24/06/25 | 3 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Pemberley Chase - Houses | 04/06/25 | 18/06/25 | 2 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Scotts Farm Road - Houses | 04/06/25 | 09/06/25 | 1 week | Complete |  |  |  |  | 2025-12-22: Christmas Break
Holman Road - Houses | 16/06/25 | 01/07/25 | 2 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Rowden Road - Houses | 16/06/25 | 01/07/25 | 2 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Cox Lane - Houses | 16/06/25 | 30/06/25 | 2 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Hogsmill Way - Houses | 16/06/25 | 30/06/25 | 2 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Millaise Way - Houses | 16/06/25 | 30/06/25 | 2 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Baker Place -House | 09/07/25 | 15/07/25 | 1 week | Complete |  |  |  |  | 2025-12-22: Christmas Break
Alway Avenue - Houses | 09/07/25 | 16/07/25 | 1 week | Complete |  |  |  |  | 2025-12-22: Christmas Break
Ruxley Lane - House | 09/07/25 | 15/07/25 | 1 week | Complete |  |  |  |  | 2025-12-22: Christmas Break
Mortimer Crescent - House | 09/07/25 | 15/07/25 | 1 week | Complete |  |  |  |  | 2025-12-22: Christmas Break
Bishopstone Walk - Houses | 09/07/25 | 22/07/25 | 2 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Cremorne Gardens - Houses | 09/07/25 | 22/07/25 | 2 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Orlando Gardens - Houses | 09/07/25 | 22/07/25 | 2 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Daisy Meadow - Houses | 14/07/25 | 28/07/25 | 2 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Daisy Meadow 6-18 - Flats | 14/07/25 | 28/07/25 | 2 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Eleanor Avenue 36-47- Flats | 14/07/25 | 28/07/25 | 2 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
James Court 1-4, Baker Place - Flats | 14/07/25 | 28/07/25 | 2 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Middleton Road 11-22 (Flats) | 23/07/25 | 05/08/25 | 2 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Mole Court - Houses | 24/07/25 | 06/08/25 | 2 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Bishopsmead Court 1-14 - Flats | 28/07/25 | 07/08/25 | 2 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Rutland Close 30-39 - Flats | 29/07/25 | 08/08/25 | 2 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Pemberley House 1-12 - Flats | 31/07/25 | 11/08/25 | 2 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Middleton Road - Houses | 05/08/25 | 18/08/25 | 2 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Westmorland Close -House | 05/08/25 | 18/08/25 | 2 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Hillingdale - Houses | 06/08/25 | 19/08/25 | 2 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Woodwards - Houses | 06/08/25 | 19/08/25 | 2 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Kenilworth Close - House | 06/08/25 | 11/08/25 | 1 week | Complete |  |  |  |  | 2025-12-22: Christmas Break
Greenways Walk - Houses | 07/08/25 | 20/08/25 | 2 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Hedgeside - House | 07/08/25 | 12/08/25 | 1 week | Complete |  |  |  |  | 2025-12-22: Christmas Break
Hollingbourne Crescent - Houses | 07/08/25 | 20/08/25 | 2 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Detling Road - House | 07/08/25 | 12/08/25 | 1 week | Complete |  |  |  |  | 2025-12-22: Christmas Break
Oakapple Close - Houses | 07/08/58 | 20/08/25 | 2 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Gorse Close - House | 07/08/25 | 14/08/25 | 1 week | Complete |  |  |  |  | 2025-12-22: Christmas Break
Guernsey Close - Houses | 07/08/25 | 20/08/25 | 2 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Wey Court 1-24 - Flats | 11/08/25 | 22/08/25 | 2 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Little Stanford Close 1-8 - Flats | 13/08/25 | 25/08/25 | 2 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Leybourne Close - House | 14/08/25 | 22/08/25 | 1 week | Complete |  |  |  |  | 2025-12-22: Christmas Break
Chaldon Road - House | 14/08/25 | 22/08/25 | 1 week | Complete |  |  |  |  | 2025-12-22: Christmas Break
St Brelades Road - Houses | 14/08/25 | 29/08/25 | 2 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
St Aubins Close - House | 14/08/25 | 22/08/25 | 1 week | Complete |  |  |  |  | 2025-12-22: Christmas Break
St Sampson Road - House | 14/08/25 | 25/08/25 | 1 week | Complete |  |  |  |  | 2025-12-22: Christmas Break
Wilmington Close - Houses | 18/08/25 | 29/08/25 | 2 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Prestwick Close - House | 18/08/25 | 22/08/25 | 1 week | Complete |  |  |  |  | 2025-12-22: Christmas Break
Kirdford Close - House | 18/08/25 | 22/08/25 | 1 week | Complete |  |  |  |  | 2025-12-22: Christmas Break
Guinevere Road - Houses | 18/08/25 | 29/08/25 | 2 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Poynings Road - House | 18/08/25 | 23/08/25 | 1 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Birkdale Drive - Houses | 18/08/25 | 29/08/25 | 2 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Nesbit Court - Flats | 18/08/25 | 29/08/25 | 2 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Chichester Close - House | 01/09/25 | 08/09/25 | 1 week | Complete |  |  |  |  | 2025-12-22: Christmas Break
Ash Keys - House | 01/09/25 | 08/09/25 | 1 week | Complete |  |  |  |  | 2025-12-22: Christmas Break
Peterlee Walk - House | 01/09/25 | 08/09/25 | 1 week | Complete |  |  |  |  | 2025-12-22: Christmas Break
Leveret Lane - House | 01/09/25 | 08/09/25 | 1 week | Complete |  |  |  |  | 2025-12-22: Christmas Break
Jewel Walk - House | 01/09/25 | 08/09/25 | 1 week | Complete |  |  |  |  | 2025-12-22: Christmas Break
Brettingham Close - House | 01/09/25 | 08/09/25 | 1 week | Complete |  |  |  |  | 2025-12-22: Christmas Break
Gossops Drive - House | 01/09/25 | 08/09/25 | 1 week | Complete |  |  |  |  | 2025-12-22: Christmas Break
Rother Crescent - House | 01/09/25 | 08/09/25 | 1 week | Complete |  |  |  |  | 2025-12-22: Christmas Break
Bolney Court - House | 01/09/25 | 08/09/25 | 1 week | Complete |  |  |  |  | 2025-12-22: Christmas Break
Donnington Court - House | 01/09/25 | 08/09/25 | 1 week | Complete |  |  |  |  | 2025-12-22: Christmas Break
Burbeach Close - Houses | 01/09/25 | 12/09/25 | 2 weeks | Complete |  |  |  |  | 2025-12-22: Christmas Break
Dampier Walk - House | 01/09/25 | 05/09/25 | 1 week | Complete |  |  |  |  | 2025-12-22: Christmas Break
Sandringham Road - House | 01/09/25 | 05/09/25 | 1 week | Complete |  |  |  |  | 2025-12-22: Christmas Break
Buchans Lawn - House | 01/09/25 | 05/09/25 | 1 week | Complete |  |  |  |  | 2025-12-22: Christmas Break
Ash Court 1-12, 25-36 - Flats | 03/09/25 |  |  | On hold/awaiting further instruction |  |  |  |  | 2025-12-22: Christmas Break
Norman Colyer Court - Flats 3-52 | 15/09/25 |  |  | Lounge & porch o/s |  |  |  |  | 2025-12-22: Christmas Break
Teddington Close Flats 1-8 (mixed) | 17/11/25 | by 05/12/25 | [6 empty] | 2025-12-22: Christmas Break
Teddington Close - Flats 9-12 | 17/11/25 | by 05/12/25 | [6 empty] | 2025-12-22: Christmas Break
Teddington Close - Flats 14-17 | 17/11/25 | by 05/12/25 | [6 empty] | 2025-12-22: Christmas Break
Teddington Close - Flats 18-25 | 17/11/25 | by 05/12/25 | [6 empty] | 2025-12-22: Christmas Break
Teddington Close - Flats 26-33 | 17/11/25 | by 05/12/25 | [6 empty] | 2025-12-22: Christmas Break
Scotts Farm Road - Flats 51-57 (odds) | 17/11/25 | by 05/12/25 | [6 empty] | 2025-12-22: Christmas Break
Scotts Farm Road - Flats 59-65 (odds) | 17/11/25 | by 05/12/25 | [6 empty] | 2025-12-22: Christmas Break
Scotts Farm Road - Flats 67-73 (odds) | 17/11/25 | by 05/12/25 | [6 empty] | 2025-12-22: Christmas Break
Scotts Farm Road - Flats 58-64 (evens) | 17/11/25 | by 05/12/25 | [6 empty] | 2025-12-22: Christmas Break
Ruxley Court - Flats 1-12 | 19/11/25 | by 05/12/25 | [6 empty] | 2025-12-22: Christmas Break
James Court - Flats 5-8 | 24/11/25 | [7 empty] | 2025-12-22: Christmas Break
Albert House - Flats 1-6 | 03/12/25 | [7 empty] | 2025-12-22: Christmas Break
Cromwell - Flats 38-44 | 04/12/25 | [7 empty] | 2025-12-22: Christmas Break
Gadesden Road - Flats 37-38a | 05/12/25 | [7 empty] | 2025-12-22: Christmas Break
Hollymoor Lane - Flats 81-99 | 08/11/25 | [7 empty] | 2025-12-22: Christmas Break
Hollymoor Lane - Flats 117-139 | 08/11/25 | [7 empty] | 2025-12-22: Christmas Break
Somerset Close - Flats 8-16 | 11/12/25 | [7 empty] | 2025-12-22: Christmas Break
Somerset Close - Flats 17-22 | 11/12/25 | [7 empty] | 2025-12-22: Christmas Break
Watersedge Estate - Colne | Jan 26 | [7 empty] | 2025-12-22: Christmas Break; 2026-01-05: tbc; 2026-01-12: tbc; 2026-01-19: tbc; 2026-01-26: tbc
Watersedge Estate - Ashmead | Jan 26 | [7 empty] | 2025-12-22: Christmas Break; 2026-01-05: tbc; 2026-01-12: tbc; 2026-01-19: tbc; 2026-01-26: tbc
Watersedge Estate - Mole | Jan 26 | [7 empty] | 2025-12-22: Christmas Break; 2026-01-05: tbc; 2026-01-12: tbc; 2026-01-19: tbc; 2026-01-26: tbc
Watersedge Estate - Wandle | Jan 26 | [7 empty] | 2025-12-22: Christmas Break; 2026-01-05: tbc; 2026-01-12: tbc; 2026-01-19: tbc; 2026-01-26: tbc
Watersedge Estate - Wey | Jan 26 | [7 empty] | 2025-12-22: Christmas Break; 2026-01-05: tbc; 2026-01-12: tbc; 2026-01-19: tbc; 2026-01-26: tbc
Sefton Road - Houses | tbc | [7 empty] | 2025-12-22: Christmas Break; 2026-01-05: tbc; 2026-01-12: tbc; 2026-01-19: tbc; 2026-01-26: tbc
Curtis Road | tbc | [7 empty] | 2025-12-22: Christmas Break; 2026-01-05: tbc; 2026-01-12: tbc; 2026-01-19: tbc; 2026-01-26: tbc
Rosebank Flats (Mixed LH & GN Blocks) | Feb/Mar 2026 |  |  | Est. start end of Fin. Year |  |  |  |  | 2025-12-22: Christmas Break; 2026-02-02: tbc; 2026-02-09: tbc

## Roof (hidden)
Town & Country - 2025/26 Works Programme |  | as at 04/11/25
ROOF WORKS
Key:
In Progress
Estimated Start
Complete
[5 empty] | Week1 | Week2 | Week3 | Week4 | Week5 | Week7 | Week8 | Week9 | Week10 | Week11 | Week12 | Week13 | Week14 | Week15 | Week16 | Week17 | Week18 | Week19 | Week20 | Week21 | Week22 | Week23 | Week24 | Week25 | Week26 | Week27 | Week28 | Week29 | Week30 | Week31 | Week32 | Week33 | Week34 | Week35 | Week36 | Week37 | Week38 | Week39 | Week40 | Week41 | Week42 | Week43 | Week44 | Week45 | Week46 | Week47 | Week48 | Week49 | Week50 | Week51 | Week52 | Week53
Property | Start Date | End Date | Duration | Status / comment | 2025-04-07 | 2025-04-14 | 2025-04-21 | 28/04/25 | time axis 2025-05-05 to 2026-03-30
Norman Colyer Court 1-52 | 01/09/25 | by 12/12/25 |  | In progress |  |  |  |  | 2025-12-08: Strike Scaff; 2025-12-22: Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Nursery (Adj. Norman Colyer) | 06/12/25 | by 19/12/25 |  | Front first, then sides and back |  |  |  |  | 2025-12-01: Scaff up; 2025-12-15: Strike scaff; 2025-12-22: Christmas Break

## Roofline (hidden)
Town & Country - 2025/26 Works Programme |  | as at 04/12/25
ROOFLINE WORKS
Key:
In Progress
Estimated Start
Complete
[5 empty] | Week1 | Week2 | Week3 | Week4 | Week5 | Week7 | Week8 | Week9 | Week10 | Week11 | Week12 | Week13 | Week14 | Week15 | Week16 | Week17 | Week18 | Week19 | Week20 | Week21 | Week22 | Week23 | Week24 | Week25 | Week26 | Week27 | Week28 | Week29 | Week30 | Week31 | Week32 | Week33 | Week34 | Week35 | Week36 | Week37 | Week38 | Week39 | Week40 | Week41 | Week42 | Week43 | Week44 | Week45 | Week46 | Week47 | Week48 | Week49 | Week50 | Week51 | Week52 | Week53
Property | Start Date | End Date | Duration | Status / comment | 2025-04-07 | 2025-04-14 | 2025-04-21 | 28/04/25 | time axis 2025-05-05 to 2026-03-30
Hogsmill Way 47 | 28/07/25 | 29/08/25 |  | Complete |  |  |  |  | 2025-12-22: Christmas Break
Hogsmill Way 49 | 28/07/25 | 29/08/25 |  | Complete |  |  |  |  | 2025-12-22: Christmas Break
Millais Way 2 | 28/07/25 | 29/08/25 |  | Complete |  |  |  |  | 2025-12-22: Christmas Break
Millais Way 13 | 28/07/25 | 29/08/25 |  | Complete |  |  |  |  | 2025-12-22: Christmas Break
Millais Way 14 | 28/07/25 | 29/08/25 |  | Complete |  |  |  |  | 2025-12-22: Christmas Break
Watersedge 32 | 28/07/25 | 29/08/25 |  | Complete |  |  |  |  | 2025-12-22: Christmas Break
Watersedge 34 | 28/07/25 | 29/08/25 |  | Complete |  |  |  |  | 2025-12-22: Christmas Break
Millais Way 15 | 11/08/25 | 12/09/25 |  | Complete |  |  |  |  | 2025-12-22: Christmas Break
Cox Lane 14 | 06/10/25 | 14/11/25 |  | Complete |  |  |  |  | 2025-12-22: Christmas Break
Gatley Avenue 40 | 06/10/25 | 14/11/25 |  | Complete |  |  |  |  | 2025-12-22: Christmas Break
Holman Road 44 | 06/10/25 | 14/11/25 |  | Complete |  |  |  |  | 2025-12-22: Christmas Break
Holman Road 50 | 06/10/25 | 14/11/25 |  | Complete |  |  |  |  | 2025-12-22: Christmas Break
Holman Road 52 | 06/10/25 | 14/11/25 |  | Complete |  |  |  |  | 2025-12-22: Christmas Break
Holman Road 54 | 06/10/25 | 14/11/25 |  | Complete |  |  |  |  | 2025-12-22: Christmas Break
Holman Road 60 | 06/10/25 | 14/11/25 |  | Complete |  |  |  |  | 2025-12-22: Christmas Break
Holman Road 62 | 06/10/25 | 14/11/25 |  | Complete |  |  |  |  | 2025-12-22: Christmas Break
Holman Road 64 | 06/10/25 | 14/11/25 |  | Complete |  |  |  |  | 2025-12-22: Christmas Break
Rosebank 9 | 13/10/25 | 21/11/25 |  | Complete |  |  |  |  | 2025-12-22: Christmas Break
Rosebank 10 | 13/10/25 | 21/11/25 |  | Complete |  |  |  |  | 2025-12-22: Christmas Break
Rosebank 11 | 13/10/25 | 21/11/25 |  | Complete |  |  |  |  | 2025-12-22: Christmas Break
Rosebank 12 | 13/10/25 | 21/11/25 |  | Complete |  |  |  |  | 2025-12-22: Christmas Break
Rosebank 17 | 13/10/25 | 21/11/25 |  | Complete |  |  |  |  | 2025-12-22: Christmas Break
Rosebank 67 | 13/10/25 | 21/11/25 |  | Complete |  |  |  |  | 2025-12-22: Christmas Break
Ruxley Lane 134 | 13/10/25 | 14/11/25 |  | Complete |  |  |  |  | 2025-12-22: Christmas Break
Rosebank - Flats 5-8 | 20/11/25 | by 23/12/25 | [6 empty] | 2025-11-17: Scaffold up; 2025-11-24: removal; 2025-12-01: remov/renew; 2025-12-08: renewal; 2025-12-15: renew/Strike; 2025-12-22: Christmas Break
Rosebank - Flats 13-16 | 20/11/25 | by 23/12/25 | [6 empty] | 2025-11-17: Scaffold up; 2025-11-24: removal; 2025-12-01: remov/renew; 2025-12-08: renewal; 2025-12-15: renew/Strike; 2025-12-22: Christmas Break
Rosebank - Flats 31-34 | 20/11/25 | by 23/12/25 | [6 empty] | 2025-11-17: Scaffold up; 2025-11-24: removal; 2025-12-01: remov/renew; 2025-12-08: renewal; 2025-12-15: renew/Strike; 2025-12-22: Christmas Break
Rosebank - Flats 39-42 | 20/11/25 | by 23/12/25 | [6 empty] | 2025-11-17: Scaffold up; 2025-11-24: removal; 2025-12-01: remov/renew; 2025-12-08: renewal; 2025-12-15: renew/Strike; 2025-12-22: Christmas Break
Rosebank - Flats 43-46 | 20/11/25 | by 23/12/25 | [6 empty] | 2025-11-17: Scaffold up; 2025-11-24: removal; 2025-12-01: remov/renew; 2025-12-08: renewal; 2025-12-15: renew/Strike; 2025-12-22: Christmas Break
The Crescent - Flats 77-83 (odds) Asb. | Jan 26 |  |  | Awaiting Scaffold date |  |  |  |  | 2025-12-22: Christmas Break; 2026-01-05: TBC; 2026-01-12: TBC; 2026-01-19: TBC; 2026-01-26: TBC
The Crescent - Flats 85-91 (odds) | Jan 26 |  |  | Awaiting Scaffold date |  |  |  |  | 2025-12-22: Christmas Break; 2026-01-05: TBC; 2026-01-12: TBC; 2026-01-19: TBC; 2026-01-26: TBC
The Crescent - Flats 99-105 (odds) | Jan 26 |  |  | Awaiting Scaffold date |  |  |  |  | 2025-12-22: Christmas Break; 2026-01-05: TBC; 2026-01-12: TBC; 2026-01-19: TBC; 2026-01-26: TBC
The Crescent - Flats 107-113 (odds) | Jan 26 |  |  | Awaiting Scaffold date |  |  |  |  | 2025-12-22: Christmas Break; 2026-01-05: TBC; 2026-01-12: TBC; 2026-01-19: TBC; 2026-01-26: TBC
The Crescent - Flats 115-121 (odds) | Jan 26 |  |  | Awaiting Scaffold date |  |  |  |  | 2025-12-22: Christmas Break; 2026-01-05: TBC; 2026-01-12: TBC; 2026-01-19: TBC; 2026-01-26: TBC
The Crescent - Flats 70-76 (evens) | Jan 26 |  |  | Awaiting Scaffold date |  |  |  |  | 2025-12-22: Christmas Break; 2026-01-05: TBC; 2026-01-12: TBC; 2026-01-19: TBC; 2026-01-26: TBC
The Crescent - Flats 86-92 (evens) | Jan 26 |  |  | Awaiting Scaffold date |  |  |  |  | 2025-12-22: Christmas Break; 2026-01-05: TBC; 2026-01-12: TBC; 2026-01-19: TBC; 2026-01-26: TBC
Rushmere Court Flats 1-6 | Jan 26 | [7 empty] | 2025-12-22: Christmas Break; 2026-01-05: TBC; 2026-01-12: TBC; 2026-01-19: TBC; 2026-01-26: TBC
Rushmere Court Flats 7-12 | Jan 26 | [7 empty] | 2025-12-22: Christmas Break; 2026-01-05: TBC; 2026-01-12: TBC; 2026-01-19: TBC; 2026-01-26: TBC
Rushmere Court Flats 13-18 | Jan 26 | [7 empty] | 2025-12-22: Christmas Break; 2026-01-05: TBC; 2026-01-12: TBC; 2026-01-19: TBC; 2026-01-26: TBC
Rushmere Court Flats 19-24 | Jan 26 | [7 empty] | 2025-12-22: Christmas Break; 2026-01-05: TBC; 2026-01-12: TBC; 2026-01-19: TBC; 2026-01-26: TBC
Rushmere Court Flats 25-30 | Jan 26 | [7 empty] | 2025-12-22: Christmas Break; 2026-01-05: TBC; 2026-01-12: TBC; 2026-01-19: TBC; 2026-01-26: TBC
Watersedge Estate - Colne | Jan 26 | [7 empty] | 2025-12-22: Christmas Break; 2026-01-05: TBC; 2026-01-12: TBC; 2026-01-19: TBC; 2026-01-26: TBC
Watersedge Estate - Ashmead | Jan 26 | [7 empty] | 2025-12-22: Christmas Break; 2026-01-05: TBC; 2026-01-12: TBC; 2026-01-19: TBC; 2026-01-26: TBC
Watersedge Estate - Mole | Jan 26 | [7 empty] | 2025-12-22: Christmas Break; 2026-01-05: TBC; 2026-01-12: TBC; 2026-01-19: TBC; 2026-01-26: TBC
Watersedge Estate - Wandle | Jan 26 | [7 empty] | 2025-12-22: Christmas Break; 2026-01-05: TBC; 2026-01-12: TBC; 2026-01-19: TBC; 2026-01-26: TBC
Watersedge Estate - Wey | Jan 26 | [7 empty] | 2025-12-22: Christmas Break; 2026-01-05: TBC; 2026-01-12: TBC; 2026-01-19: TBC; 2026-01-26: TBC
[42 empty] | GJ Christmas Break |  | TBC
[42 empty] | GJ Christmas Break |  | TBC
[42 empty] | GJ Christmas Break |  | TBC
[42 empty] | GJ Christmas Break |  | TBC
[42 empty] | GJ Christmas Break |  | TBC
[42 empty] | GJ Christmas Break |  | TBC
[42 empty] | Christmas Break |  | TBC | TBC | TBC | TBC

## Asbestos (hidden)
Town & Country - 2025/26 Works Programme |  | as at 30/11/25
ASBESTOS WORKS
Key:
In Progress
Estimated Start
Complete
[5 empty] | Week1 | Week2 | Week3 | Week4 | Week5 | Week7 | Week8 | Week9 | Week10 | Week11 | Week12 | Week13 | Week14 | Week15 | Week16 | Week17 | Week18 | Week19 | Week20 | Week21 | Week22 | Week23 | Week24 | Week25 | Week26 | Week27 | Week28 | Week29 | Week30 | Week31 | Week32 | Week33 | Week34 | Week35 | Week36 | Week37 | Week38 | Week39 | Week40 | Week41 | Week42 | Week43 | Week44 | Week45 | Week46 | Week47 | Week48 | Week49 | Week50 | Week51 | Week52 | Week53
Property | Start Date | End Date | Duration | Status / comment | 2025-04-07 | 2025-04-14 | 2025-04-21 | 28/04/25 | time axis 2025-05-05 to 2026-03-30
Cox Lane 14 | 06/10/25 | [7 empty] | 2025-10-06: Scaffold up; 2025-10-13: soffit removal; 2025-10-20: soffit removal; 2025-10-27: roofline renew; 2025-11-03: roofline renew; 2025-11-10: Strike scaff; 2025-12-22: Christmas Break
Gatley Avenue 40 | 06/10/25 | [7 empty] | 2025-10-06: Scaffold up; 2025-10-13: soffit removal; 2025-10-20: soffit removal; 2025-10-27: roofline renew; 2025-11-03: roofline renew; 2025-11-10: Strike scaff; 2025-12-22: Christmas Break
Holman Road 44 | 06/10/25 | [7 empty] | 2025-10-06: Scaffold up; 2025-10-13: soffit removal; 2025-10-20: soffit removal; 2025-10-27: roofline renew; 2025-11-03: roofline renew; 2025-11-10: Strike scaff; 2025-12-22: Christmas Break
Holman Road 50 | 06/10/25 | [7 empty] | 2025-10-06: Scaffold up; 2025-10-13: soffit removal; 2025-10-20: soffit removal; 2025-10-27: roofline renew; 2025-11-03: roofline renew; 2025-11-10: Strike scaff; 2025-12-22: Christmas Break
Holman Road 52 | 06/10/25 | [7 empty] | 2025-10-06: Scaffold up; 2025-10-13: soffit removal; 2025-10-20: soffit removal; 2025-10-27: roofline renew; 2025-11-03: roofline renew; 2025-11-10: Strike scaff; 2025-12-22: Christmas Break
Holman Road 54 | 06/10/25 | [7 empty] | 2025-10-06: Scaffold up; 2025-10-13: soffit removal; 2025-10-20: soffit removal; 2025-10-27: roofline renew; 2025-11-03: roofline renew; 2025-11-10: Strike scaff; 2025-12-22: Christmas Break
Holman Road 60 | 06/10/25 | [7 empty] | 2025-10-06: Scaffold up; 2025-10-13: soffit removal; 2025-10-20: soffit removal; 2025-10-27: roofline renew; 2025-11-03: roofline renew; 2025-11-10: Strike scaff; 2025-12-22: Christmas Break
Holman Road 62 | 06/10/25 | [7 empty] | 2025-10-06: Scaffold up; 2025-10-13: soffit removal; 2025-10-20: soffit removal; 2025-10-27: roofline renew; 2025-11-03: roofline renew; 2025-11-10: Strike scaff; 2025-12-22: Christmas Break
Holman Road 64 | 06/10/25 | [7 empty] | 2025-10-06: Scaffold up; 2025-10-13: soffit removal; 2025-10-20: soffit removal; 2025-10-27: roofline renew; 2025-11-03: roofline renew; 2025-11-10: Strike scaff; 2025-12-22: Christmas Break
Ruxley Lane 134 | 13/10/25 | [7 empty] | 2025-10-13: Scaffold up; 2025-10-20: soffit removal; 2025-10-27: soffit removal; 2025-11-03: Roofline renew; 2025-11-10: Roofline renew; 2025-11-17: Strike scaff; 2025-12-22: Christmas Break
Rosebank 9 | 13/10/25 | [7 empty] | 2025-10-13: Scaffold up; 2025-10-20: Soffit removal; 2025-10-27: soffit removal; 2025-11-03: Roofline renew; 2025-11-10: Roofline renew; 2025-11-17: Strike scaff; 2025-12-22: Christmas Break
Rosebank 10 | 13/10/25 | [7 empty] | 2025-10-13: Scaffold up; 2025-10-20: Soffit removal; 2025-10-27: soffit removal; 2025-11-03: Roofline renew; 2025-11-10: Roofline renew; 2025-11-17: Strike scaff; 2025-12-22: Christmas Break
Rosebank 11 | 13/10/25 | [7 empty] | 2025-10-13: Scaffold up; 2025-10-20: Soffit removal; 2025-10-27: soffit removal; 2025-11-03: Roofline renew; 2025-11-10: Roofline renew; 2025-11-17: Strike scaff; 2025-12-22: Christmas Break
Rosebank 12 | 13/10/25 | [7 empty] | 2025-10-13: Scaffold up; 2025-10-20: Soffit removal; 2025-10-27: soffit removal; 2025-11-03: Roofline renew; 2025-11-10: Roofline renew; 2025-11-17: Strike scaff; 2025-12-22: Christmas Break
Rosebank 17 | 13/10/25 | [7 empty] | 2025-10-13: Scaffold up; 2025-10-20: Soffit removal; 2025-10-27: soffit removal; 2025-11-03: Roofline renew; 2025-11-10: Roofline renew; 2025-11-17: Strike scaff; 2025-12-22: Christmas Break
Rosebank 67 | 13/10/25 | [7 empty] | 2025-10-13: Scaffold up; 2025-10-20: Soffit removal; 2025-10-27: soffit removal; 2025-11-03: Roofline renew; 2025-11-10: Roofline renew; 2025-11-17: Strike scaff; 2025-12-22: Christmas Break
Rosebank 68 | 13/10/25 | [7 empty] | 2025-10-13: Scaffold up; 2025-10-20: Soffit removal; 2025-10-27: soffit removal; 2025-11-03: Roofline renew; 2025-11-10: Roofline renew; 2025-11-17: Strike scaff; 2025-12-22: Christmas Break
Rosebank - Flats 5-8 | 20/11/25 | by 23/12/25 | [6 empty] | 2025-11-17: Scaffold up; 2025-11-24: removal; 2025-12-01: removal; 2025-12-08: renewal; 2025-12-15: renew/Strike; 2025-12-22: Christmas Break
Rosebank - Flats 13-16 | 20/11/25 | by 23/12/25 | [6 empty] | 2025-11-17: Scaffold up; 2025-11-24: removal; 2025-12-01: removal; 2025-12-08: renewal; 2025-12-15: renew/Strike; 2025-12-22: Christmas Break
Rosebank - Flats 31-34 | 20/11/25 | by 23/12/25 | [6 empty] | 2025-11-17: Scaffold up; 2025-11-24: removal; 2025-12-01: removal; 2025-12-08: renewal; 2025-12-15: renew/Strike; 2025-12-22: Christmas Break
Rosebank - Flats 39-42 | 20/11/25 | by 23/12/25 | [6 empty] | 2025-11-17: Scaffold up; 2025-11-24: removal; 2025-12-01: removal; 2025-12-08: renewal; 2025-12-15: renew/Strike; 2025-12-22: Christmas Break
Rosebank - Flats 43-46 | 20/11/25 | by 23/12/25 | [6 empty] | 2025-11-17: Scaffold up; 2025-11-24: removal; 2025-12-01: removal; 2025-12-08: renewal; 2025-12-15: renew/Strike; 2025-12-22: Christmas Break
The Crescent - Flats 77-83 (odds) | 05/01/26 | [7 empty] | 2025-12-22: Christmas Break
The Crescent - Flats 85-91 (odds) | 05/01/26 | [7 empty] | 2025-12-22: Christmas Break
The Crescent - Flats 99-105 (odds) | 05/01/26 | [7 empty] | 2025-12-22: Christmas Break
The Crescent - Flats 107-113 (odds) | 05/01/26 | [7 empty] | 2025-12-22: Christmas Break
The Crescent - Flats 115-121 (odds) | 05/01/26 | [7 empty] | 2025-12-22: Christmas Break
The Crescent - Flats 70-76 (evens) | 05/01/26 | [7 empty] | 2025-12-22: Christmas Break
The Crescent - Flats 86-92 (evens) | 05/01/26 | [7 empty] | 2025-12-22: Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break

## Tarmac etc (hidden)
Town & Country - 2025/26 Works Programme |  | as at 04/12/25
FLOORING
Key:
In Progress
Estimated Start
Complete
[5 empty] | Week1 | Week2 | Week3 | Week4 | Week5 | Week7 | Week8 | Week9 | Week10 | Week11 | Week12 | Week13 | Week14 | Week15 | Week16 | Week17 | Week18 | Week19 | Week20 | Week21 | Week22 | Week23 | Week24 | Week25 | Week26 | Week27 | Week28 | Week29 | Week30 | Week31 | Week32 | Week33 | Week34 | Week35 | Week36 | Week37 | Week38 | Week39 | Week40 | Week41 | Week42 | Week43 | Week44 | Week45 | Week46 | Week47 | Week48 | Week49 | Week50 | Week51 | Week52 | Week53
Property | Start Date | End Date | Duration | Status / comment | 2025-04-07 | 2025-04-14 | 2025-04-21 | 28/04/25 | time axis 2025-05-05 to 2026-03-30
John Gale Court | 18/08/25 | 29/08/25 | 2 weeks | Carpark Flooring Complete |  |  |  |  | 2025-12-22: Christmas Break
Norman Colyer | TBC |  |  | Shelter TBC |  |  |  |  | 2025-12-22: Christmas Break; 2026-01-05: tbc; 2026-01-12: tbc; 2026-01-19: tbc; 2026-01-26: tbc
Teddington Close Alleyway | TBC |  |  | Tarmac |  |  |  |  | 2025-12-22: Christmas Break; 2026-01-05: tbc; 2026-01-12: tbc; 2026-01-19: tbc; 2026-01-26: tbc
Scotts Farm Road | Jan 26 |  |  | Tarmac |  |  |  |  | 2025-12-22: Christmas Break; 2026-01-05: tbc; 2026-01-12: tbc; 2026-01-19: tbc; 2026-01-26: tbc

## TEMPLATE (hidden)
Town & Country - 2025/26 Works Programme |  | as at 30/09/25
WORKS TYPE
Key:
In Progress
Estimated Start
Complete
[5 empty] | Week1 | Week2 | Week3 | Week4 | Week5 | Week7 | Week8 | Week9 | Week10 | Week11 | Week12 | Week13 | Week14 | Week15 | Week16 | Week17 | Week18 | Week19 | Week20 | Week21 | Week22 | Week23 | Week24 | Week25 | Week26 | Week27 | Week28 | Week29 | Week30 | Week31 | Week32 | Week33 | Week34 | Week35 | Week36 | Week37 | Week38 | Week39 | Week40 | Week41 | Week42 | Week43 | Week44 | Week45 | Week46 | Week47 | Week48 | Week49 | Week50 | Week51 | Week52 | Week53
Property | Start Date | End Date | Duration | Status / comment | 2025-04-07 | 2025-04-14 | 2025-04-21 | 28/04/25 | time axis 2025-05-05 to 2026-03-30
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break
Christmas Break

## Decs Alphabetical (hidden)
Addresses | Property | SOW date | End date
Almond Road - Houses | Almond Road - Houses
Alway Avenue Houses | Alway Avenue - Houses
Ash Cottages - Houses | Ash Cottages - Houses
Baker Place - House | Ash Court 1-12, 25-36 - Flats
Belfield Road - House | Ash Keys - House
Bishopsmead Close - Houses | Baker Place -House
Bishopsmead Court 1-14 (Flats) | Belfield Road - Houses
Bishopstone Walk - Houses | Birkdale Drive - Houses
Bourne Way - House | Bishopsmead Close - Houses
Brumfield Road - Houses | Bishopsmead Court 1-14 - Flats
Cherwell Court - Houses | Bishopstone Walk - Houses
Cotherstone - Houses | Bolney Court - House
Cox Lane - Houses | Bourne Way - House
Crane Court - Houses | Brettingham Close - House
Cremone Gardens - Houses | Brumfield Road - Houses
Cumberland Close - Houses | Buchans Lawn - House
Curtis Road | Burbeach Close - Houses
Daisy Meadow - Houses | Chaldon Road - House
Daisy Meadow 6-18 - Flats | Cherwell Court - Houses
Dorset Square - Houses | Chichester Close - House
Eleanor Avenue 36-47- Flats | Cotherstone - Houses
Eleanor Avenue - Houses | Cox Lane - Houses
Fendall Road - Houses | Crane Court - Houses
Gadesden Road - Houses | Cremone Gardens - Houses
Gatley Avenue - Houses | Cumberland Close - Houses
Hogsmill Way - Houses | Curtis Road
Hollymoor Lane - Houses | Daisy Meadow - Houses
Holman Road - Houses | Daisy Meadow 6-18 - Flats
Hyperion Place - Houses | Dampier Walk - House
Iris Court - House | Detling Road - House
James Court 1-4, Baker Place (Flats) | Donnington Court - House
Lansdowne Road - House | Dorset Square - Houses
Lincoln Walk - Houses | Eleanor Avenue - Houses
Melton Place - Houses | Eleanor Avenue 36-47- Flats
Middleton Road 11-22 (Flats) | Fendall Road - Houses
Millaise Way - Houses | Gadesden Road - Houses
Mole Court - Houses | Gatley Avenue - Houses
Mortimer Crescent - House | Gorse Close - House
Orlando Gardens - Houses | Gossops Drive - House
Ormonde Avenue - Houses | Greenways Walk - Houses
Pemberley Chase - Houses | Guernsey Close - Houses
Pemberley House 1-12, Pemberley Chase (Flats) | Guinevere Road - Houses
Rosebank Houses | Hedgeside - House
Rowden Road - Houses | Hillingdale - Houses (excl no.5)
Rutland Close - Houses | Hogsmill Way - Houses
Rutland Close 30-39 (Flats) | Hollingbourne Crescent - Houses
Ruxley Lane 134 - House | Hollymoor Lane - Houses
Scott Close - Houses | Holman Road - Houses
Scotts Farm Road - Houses | Hyperion Place - Houses
Sefton Road - Houses | Iris Court - House
Shawford Road - Houses | James Court 1-4, Baker Place - Flats
Somerset Close - Houses | Jewel Walk - House
Trigo Court - Houses | Kenilworth Close - House
Watersedge - Houses | Kirdford Close - House
Lansdowne Road - House
Leveret Lane - House
Leybourne Close - House
Lincoln Walk - Houses
Little Stanford Close 1-8 - Flats
Melton Place - Houses
Middleton Road - Houses
Middleton Road 11-22 (Flats)
Millaise Way - Houses
Mole Court - Houses
Mortimer Crescent - House
Nesbit Court - Flat
Norman Colyer Court 1-22 (Gr/Flr Flats)
Norman Colyer Court 23-37 (1st/Flr Flats)
Norman Colyer Court 38-52 (2nd/Flr Flats)
Oakapple Close - Houses
Orlando Gardens - Houses
Ormonde Avenue - Houses
Pemberley Chase - Houses
Pemberley House 1-12 - Flats
Peterlee Walk - House
Poynings Road - House
Prestwick Close - House
Rosebank - Houses
Rother Crescent - House
Rowden Road - Houses
Rutland Close - Houses
Rutland Close 30-39 - Flats
Ruxley Lane - House
Sandringham Road - House
Scott Close - Houses
Scotts Farm Road - Houses
Sefton Road - Houses
Shawford Road - Houses
Somerset Close - Houses
St Andrews Road - House
St Aubins Close - House
St Brelades Road - Houses
St Sampson Road - House
Trigo Court - Houses
Watersedge - Houses
Westmorland Close -House
Wey Court 1-24 - Flats
Wilmington Close - Houses
Woodwards - Houses